## GTM Content Roadmap
AI-Native Data Foundation & Autonomous Ops — Sales Offering Content Build Roadmap
Playbook · Proposals · Case Studies · Solution Deliverables · Code Templates · Learning Modules · Asset Catalog
# | Workstream | Task | Detailed Description | Owner | Month 1 | Month 2 | Month 3 | Month 4 | Status
OFFERING MASTER PLAYBOOK
1 | Offering Master Playbook | Offering Narrative & Value Proposition | Craft the elevator pitch, executive summary, 3 core differentiators, and competitive positioning statement for the unified offering. Include versions for CTO, CDO, and VP Data personas. | GTM Lead | ██████ | ██████ |  |  | In Progress 1. Master Playbook/Agentic_Data_Platform_Strategic_Positioning.docx
2 | Offering Master Playbook | Ideal Customer Profile (ICP) & Buyer Personas | Document target verticals (Global Retail, Banking/FS, Manufacturing, Tech/SaaS, Large Enterprise), define buyer personas with goals/pain points, and create qualification criteria per segment. | Sales Enablement | ██████ | ██████ |  |  | Not Started
3 | Offering Master Playbook | Pricing, Packaging & Commercial Framework | Define tiered engagement models ($750K–$1.5M+), phased delivery options (Foundation Only vs Full Stack), SOW commercial terms, and discount/approval guardrails. | Practice Lead |  | ██████ |  |  | Not Started
4 | Offering Master Playbook | Sales Qualification & Discovery Playbook | Create MEDDPICC-aligned qualification framework, 25+ discovery questions per persona, technical deep-dive agenda template, and POC/pilot scoping guide. | Sales Enablement |  | ██████ | ██████ |  | Not Started
5 | Offering Master Playbook | Competitive Battle Cards | Develop battle cards for 5+ competitor types (legacy SIs, cloud-native boutiques, hyperscaler PSOs, offshore firms, DIY). Include win themes, landmines, trap-setting questions, and proof points. | GTM Lead |  |  | ██████ |  | Not Started
6 | Offering Master Playbook | Objection-Handling Guide | Catalog top 15–20 objections (budget, timing, build-vs-buy, incumbent loyalty) with structured responses, supporting data, and pivot strategies. | Sales Enablement |  |  | ██████ | ██████ | Not Started
PROPOSAL MATERIALS
7 | Proposal Materials | Executive Pitch Deck (12–15 slides) | Story-driven presentation: market context → client pain → offering overview → architecture visual → value delivered → proof points → engagement model → call-to-action. Customizable per vertical. | Marketing | ██████ | ██████ |  |  | Not Started
8 | Proposal Materials | Technical Architecture Presentation | Detailed technical deck: Medallion architecture deep-dive, vector storage & RAG layers, streaming patterns, self-healing framework, AIOps components, FinOps agents — all with polished diagrams. | Solutions Architect |  | ██████ | ██████ |  | Not Started
9 | Proposal Materials | Master SOW / Proposal Template | Reusable Statement of Work: standard phases & milestones, deliverables matrix, RACI chart, assumptions/exclusions, risk register, change control, and commercial terms. Pre-filled for 3 engagement tiers. | Delivery Lead |  | ██████ | ██████ |  | Not Started
10 | Proposal Materials | ROI Calculator & Business Case Builder | Interactive Excel/one-pager that prospects can co-fill: inputs for current spend, headcount, MTTR, downtime costs → outputs quantifying FinOps savings, productivity gains, and risk reduction. | FinOps Analyst |  |  | ██████ | ██████ | Not Started
11 | Proposal Materials | Vertical-Specific One-Pagers (Leave-Behinds) | Visually compelling single-page summaries for Retail, Banking, Manufacturing, and Tech/SaaS — each highlighting vertical-specific pain, solution approach, and 3 headline metrics. | Marketing |  |  | ██████ |  | Not Started
12 | Proposal Materials | Executive Summary Email Templates | Pre-written outreach and follow-up email sequences for post-meeting, post-POC, and proposal follow-up — customizable per persona and vertical. | Sales Enablement |  |  | ██████ | ██████ | Not Started
CASE STUDIES & PROOF POINTS
13 | Case Studies | Identify & Interview Past Project Champions | Select 3–5 strongest prior engagements across verticals, interview delivery leads and client sponsors, extract quantified outcomes (cost savings %, MTTR reduction, velocity gains, uptime improvement). | Delivery Lead | ██████ | ██████ |  |  | Not Started
14 | Case Studies | Write Formal Case Studies (2–3 pages each) | Produce polished Challenge → Solution → Architecture → Results case studies with data callouts, architecture before/after diagrams, and client quotes (anonymized if needed). Target: 3 minimum. | Technical Writer |  | ██████ | ██████ |  | Not Started
15 | Case Studies | Quick-Reference Success Snapshots | One-slide or half-page metric-heavy snapshots for each case study — designed for embedding in pitch decks, proposals, and one-pagers. Visual, scannable, executive-friendly. | Marketing |  |  | ██████ | ██████ | Not Started
16 | Case Studies | Reference Architecture Diagrams Library | Create 4–6 high-quality, reusable architecture diagrams from real wins showing before/after states, technology stack placement, and data flow — usable across proposals and decks. | Solutions Architect |  |  | ██████ | ██████ | Not Started
17 | Case Studies | Testimonial & Quote Bank | Compile a searchable bank of client quotes, stakeholder testimonials, and NPS/satisfaction data points organized by vertical, outcome type, and persona for easy proposal insertion. | Sales Enablement |  |  |  | ██████ | Not Started
BEST SOLUTION DELIVERABLES
18 | Solution Deliverables | Collect Top Deliverables from Past Engagements | Gather the highest-quality solution design documents, HLDs, LLDs, data models, pipeline specifications, migration plans, and test strategies from the 5 best prior projects. | Delivery Lead | ██████ | ██████ |  |  | Not Started
19 | Solution Deliverables | Templatize Solution Design Documents | Standardize collected deliverables into reusable templates with placeholder sections, consistent formatting, and fill-in guidance: HLD Template, LLD Template, Data Model Template, Migration Runbook, Test Strategy. | Solutions Architect |  | ██████ | ██████ | ██████ | Not Started
20 | Solution Deliverables | Vertical Accelerator Starter Kits | Package vertical-specific kits (Retail, Banking, Manufacturing) containing pre-built data models, sample KPI definitions, reference pipeline designs, and compliance checklists. | Practice Lead |  |  | ██████ | ██████ | Not Started
21 | Solution Deliverables | Sample Project Plan & Delivery Timeline | Create a model project plan (MS Project / Smartsheet exportable) with standard phases, task breakdown, dependencies, resource allocation, and milestones for a typical $1M engagement. | Delivery Lead |  |  |  | ██████ | Not Started
CODE & DEVELOPMENT TEMPLATES
22 | Code & Templates | Medallion Architecture Code Templates | Production-ready, parameterized code for Bronze/Silver/Gold layers: Snowflake SQL scripts, Snowpark Python notebooks, dbt model skeletons with documentation stubs and test macros. | Sr. Data Engineer |  | ██████ | ██████ |  | Not Started
23 | Code & Templates | Streaming & Real-Time Pipeline Samples | Reusable Kinesis / Glue Streaming pipeline templates with CI/CD hooks, dead-letter queue handling, exactly-once delivery patterns, and CloudWatch monitoring integration. | Data Engineer |  |  | ██████ | ██████ | Not Started
24 | Code & Templates | Self-Healing & AIOps Script Library | Versioned library of automation scripts: schema drift auto-remediation, pipeline auto-retry with exponential backoff, circuit breakers, anomaly detection model templates, and alerting integrations. | Platform Engineer |  |  | ██████ | ██████ | Not Started
25 | Code & Templates | FinOps Agent & Cost Monitoring Templates | Reusable FinOps automation: Snowflake warehouse auto-suspend scripts, cost anomaly detection queries, rightsizing recommendation agents, and spend dashboard templates. | FinOps Engineer |  |  |  | ██████ | Not Started
26 | Code & Templates | CI/CD & Infrastructure-as-Code Templates | Standard CI/CD pipeline templates (GitHub Actions / GitLab CI) for dbt deployments, Snowflake schema migrations, and Terraform/CDK modules for AWS infrastructure provisioning. | DevOps Lead |  |  | ██████ | ██████ | Not Started
LEARNING MODULES
27 | Learning Modules | Sales Enablement Training (Offering Overview) | 60-minute e-learning module: offering narrative, ICP walkthrough, pricing/packaging, discovery question practice, competitive positioning, and objection handling — with quiz and certification. | Sales Enablement |  | ██████ | ██████ |  | Not Started
28 | Learning Modules | Technical Pre-Sales Training (Architecture Deep-Dive) | Hands-on workshop module: Medallion architecture walkthrough, vector storage & RAG demo, Snowflake Cortex/Horizon capabilities, AWS integration patterns — with lab exercises. | Solutions Architect |  |  | ██████ | ██████ | Not Started
29 | Learning Modules | AIOps & Self-Healing Demo Workshop | Lab-based module where SEs can demo self-healing pipelines, anomaly detection, FinOps dashboards, and engineering copilots to prospects — includes demo environment setup guide. | Platform Engineer |  |  |  | ██████ | Not Started
30 | Learning Modules | Client Knowledge Transfer Curriculum | Structured handover package: slide decks, lab exercises, runbooks, and assessment quizzes designed to train client teams post-engagement on platform operations and ongoing optimization. | Delivery Lead |  |  |  | ██████ | Not Started
CATALOGING & SELECTING BEST-OF-BEST OFFERING ASSETS
31 | Asset Cataloging | Define Repository Structure & Taxonomy | Establish folder hierarchy, naming conventions, version control standards, and metadata tagging schema (vertical, asset type, maturity level, audience) for the master GTM repository. | Knowledge Mgmt Lead | ██████ |  |  |  | Not Started
32 | Asset Cataloging | Asset Quality Scoring Rubric | Create a weighted scoring matrix: relevance to offering (30%), reusability (25%), production quality (25%), recency (20%). Define thresholds for Gold/Silver/Bronze tier classification. | Practice Lead | ██████ | ██████ |  |  | Not Started
33 | Asset Cataloging | Score, Tag & Rank All Collected Assets | Apply the rubric to every asset produced across all workstreams. Tag with metadata, assign quality tier, and create a ranked master index with direct links. | Knowledge Mgmt Lead |  | ██████ | ██████ | ██████ | Not Started
34 | Asset Cataloging | Publish Best-of-Best Repository (v1.0) | Launch the curated repository on SharePoint/Confluence/GitHub with a searchable index page, quick-start guide, and access permissions for sales, pre-sales, and delivery teams. | GTM Lead |  |  |  | ██████ | Not Started
35 | Asset Cataloging | Governance, Refresh & Contribution Process | Define quarterly review cadence, asset retirement rules, contribution guidelines (how teams submit new assets), ownership matrix, and KPIs for repository health. | Practice Lead |  |  |  | ██████ | Not Started
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Harinath Challa - Please review

## Summary Timeline
Sales Offering Content — 4-Month Summary Timeline
Workstream | Tasks | Month 1 | Month 2 | Month 3 | Month 4 | Key Deliverables at Completion
Offering Master Playbook | 6 | ████ | ████ |  |  | Narrative, ICP, pricing, battle cards, objection guide
Proposal Materials | 6 | ████ | ████ | ████ |  | Pitch deck, tech deck, SOW, ROI calculator, one-pagers, email templates
Case Studies & Proof Points | 5 | ████ | ████ | ████ |  | 3+ case studies, snapshots, architecture diagrams, quote bank
Best Solution Deliverables | 4 | ████ | ████ | ████ |  | HLD/LLD templates, vertical starter kits, sample project plan
Code & Dev Templates | 5 |  | ████ | ████ |  | Medallion, streaming, self-healing, FinOps, CI/CD code libraries
Learning Modules | 4 |  | ████ | ████ |  | Sales training, tech workshop, demo lab, client curriculum
Asset Cataloging & Best-of-Best | 5 | ████ | ████ | ████ | ████ | Scored repository v1.0 with governance process
TOTAL: 35 Tasks across 7 Workstreams
MONTHLY FOCUS AREAS
Month 1 FOUNDATION & DISCOVERY | Establish repository structure, define offering narrative & ICP, begin collecting past project assets, start pitch deck and case study interviews.
Month 2 CORE CONTENT BUILD | Complete playbook components, write case studies, build proposal templates and SOW, start code template libraries, launch sales training module.
Month 3 ADVANCED CONTENT & POLISH | Finalize ROI calculator, complete all code libraries, build demo workshops, score and catalog all assets, create vertical starter kits.
Month 4 PUBLISH & ENABLE | Publish best-of-best repository v1.0, complete all learning modules, finalize governance process, conduct sales team launch enablement.