## GTM Content Roadmap
Agentic Knowledge Platform — Sales Offering Content Build Roadmap
Playbook · Proposals · Case Studies · Solution Deliverables · Code Templates · Learning · Asset Cataloging
# | Workstream | Task | Detailed Description | Owner | Month 1 | Month 2 | Month 3 | Month 4 | Status | Evidence / Deliverable
OFFERING MASTER PLAYBOOK
1 | Offering Master Playbook | Offering Narrative & Value Proposition | Craft the elevator pitch, executive summary, 3 core differentiators (unified knowledge layer + agent product management + governed AI), and competitive positioning statement for the Agentic Knowledge Platform. | GTM Lead | ██████ | ██████ |  |  | Complete | 01_Playbook/01_Offering_Narrative_and_Value_Proposition.docx
2 | Offering Master Playbook | Ideal Customer Profile (ICP) & Buyer Personas | Document target client profiles (enterprises with fragmented knowledge silos, companies scaling AI copilots, organizations with multi-agent needs). Define buyer personas: CDO, VP Engineering, Head of AI/ML, CTO. Map pain triggers and buying signals. | Sales Enablement | ██████ | ██████ |  |  | Complete | 01_Playbook/02_ICP_and_Buyer_Personas.docx
3 | Offering Master Playbook | Pricing, Packaging & Commercial Framework | Define tiered engagement models ($1.5M–$3.5M), phased delivery options (Knowledge Foundation phase vs. Agent Product Layer phase), and scope boundaries for each tier. | Practice Lead |  | ██████ |  |  | Complete | 01_Playbook/03_Pricing_Packaging_Commercial.docx
4 | Offering Master Playbook | Sales Qualification & Discovery Playbook | Create MEDDPICC-aligned qualification framework, 25+ discovery questions per persona, red-flag indicators, and scoring model to prioritize prospects with knowledge fragmentation and AI scaling challenges. | Sales Enablement |  | ██████ | ██████ |  | Complete | 01_Playbook/04_Sales_Qualification_and_Discovery_Playbook.docx
5 | Offering Master Playbook | Competitive Battle Cards | Develop battle cards for 5+ competitor types (legacy SIs, knowledge management vendors, AI platform startups, hyperscaler professional services). Include win themes, landmines, and counter-positioning. | GTM Lead |  |  | ██████ |  | Complete | 01_Playbook/05_Competitive_Battle_Cards.docx
6 | Offering Master Playbook | Objection-Handling Guide | Catalog top 15–20 objections (budget, timing, build-vs-buy, existing knowledge tools, agent governance skepticism) with data-backed rebuttals, client proof points, and pivot strategies. | Sales Enablement |  |  | ██████ | ██████ | Complete | 01_Playbook/06_Objection_Handling_Guide.docx
PROPOSAL MATERIALS
7 | Proposal Materials | Executive Pitch Deck (12–15 slides) | Story-driven presentation: market context → knowledge fragmentation pain → offering overview → architecture diagram → agent operating model → client wins → commercial options. Include speaker notes and appendix slides. | Marketing | ██████ | ██████ |  |  | Complete | 02_Proposal_Materials/07_Executive_Pitch_Deck.pptx
8 | Proposal Materials | Technical Architecture Presentation | Detailed technical deck: semantic knowledge modeling deep-dive, vector storage & RAG retrieval layer, multi-agent orchestration patterns, governance framework, integration architecture for Snowflake/Databricks/Fabric. | Solutions Architect |  | ██████ | ██████ |  | Complete | 02_Proposal_Materials/08_Technical_Architecture_Presentation.pptx
9 | Proposal Materials | Master SOW / Proposal Template | Reusable Statement of Work: standard phases & milestones (Phase 1: Knowledge Foundation, Phase 2: Agent Product Layer), deliverables matrix, RACI, assumptions, and change-order framework. | Delivery Lead |  | ██████ | ██████ |  | Complete | 02_Proposal_Materials/09_Master_SOW_Template_AKP.docx (modeled on GMAT Cortext SOW)
10 | Proposal Materials | ROI Calculator & Business Case Builder | Interactive Excel/one-pager that prospects can co-fill: inputs for current knowledge retrieval time, AI accuracy rates, agent deployment costs; outputs showing productivity gains, accuracy improvement, and cost savings. | Data Analyst |  |  | ██████ | ██████ | Complete | 02_Proposal_Materials/10_ROI_Calculator_App_Spec_and_Replit_Prompt.docx (web app spec + Replit prompt)
11 | Proposal Materials | Vertical-Specific One-Pagers (Leave-Behinds) | Visually compelling single-page summaries for Financial Services, Technology, Healthcare, and Professional Services verticals highlighting industry-specific knowledge challenges and agent use cases. | Marketing |  |  | ██████ |  | Complete | 02_Proposal_Materials/11a_One_Pager_Financial_Services.docx · 11b_Technology.docx · 11c_Healthcare.docx
12 | Proposal Materials | Executive Summary Email Templates | Pre-written outreach and follow-up email sequences for post-meeting, post-POC, and proposal-stage touchpoints tailored to the Agentic Knowledge Platform offering. | Sales Enablement |  |  | ██████ | ██████ | Complete | 02_Proposal_Materials/12_Executive_Summary_Email_Templates.docx
CASE STUDIES & PROOF POINTS
13 | Case Studies | Identify & Interview Past Project Champions | Select 3–5 strongest prior engagements (Presidio AI assistant, CDW Golden Contact ID, Chewy Snowflake migration, ALM data governance). Interview delivery leads and collect metrics, architecture artifacts, and client quotes. | Delivery Lead | ██████ | ██████ |  |  | Complete | 03_Case_Studies/13_Project_Champions_and_Reference_Plan.docx
14 | Case Studies | Write Formal Case Studies (2–3 pages each) | Produce polished Challenge → Solution → Architecture → Results case studies with quantified outcomes, reference architecture diagrams, and executive-ready formatting. | Technical Writer |  | ██████ | ██████ |  | Complete | 03_Case_Studies/14a_Case_Study_Hyatt.docx · 14b_Case_Study_CDW.docx · 14c_Case_Study_Vialto.docx
15 | Case Studies | Quick-Reference Success Snapshots | One-slide or half-page metric-heavy snapshots for each case study — designed for fast insertion into pitch decks and proposals. | Marketing |  |  | ██████ | ██████ | Complete | 03_Case_Studies/15_Success_Snapshots.pptx
16 | Case Studies | Reference Architecture Diagrams Library | Create 4–6 high-quality, reusable architecture diagrams from real engagements showing knowledge ingestion, semantic modeling, retrieval infrastructure, and agent orchestration patterns. | Solutions Architect |  |  | ██████ | ██████ | Not Started
17 | Case Studies | Testimonial & Quote Bank | Compile a searchable bank of client quotes, stakeholder testimonials, and satisfaction metrics across Presidio, CDW, Chewy, and ALM engagements. | Sales Enablement |  |  |  | ██████ | Not Started
BEST SOLUTION DELIVERABLES
18 | Solution Deliverables | Collect Top Deliverables from Past Engagements | Gather the highest-quality solution design documents, HLDs, LLDs, knowledge models, and agent architecture specs from Presidio, CDW, Chewy, and ALM engagements. Sanitize and redact client-specific data. | Delivery Lead | ██████ | ██████ |  |  | Not Started
19 | Solution Deliverables | Templatize Solution Design Documents | Standardize collected deliverables into reusable templates with placeholder sections for knowledge layer architecture, semantic models, agent design, governance controls, and integration patterns. | Solutions Architect |  | ██████ | ██████ | ██████ | Complete | 04_Solution_Deliverables/19_Solution_Design_Document_Template.docx
20 | Solution Deliverables | Vertical Accelerator Starter Kits | Package vertical-specific kits (Financial Services, Technology, Healthcare) containing pre-configured knowledge taxonomies, agent personas, sample retrieval patterns, and governance templates. | Practice Lead |  |  | ██████ | ██████ | Not Started
21 | Solution Deliverables | Sample Project Plan & Delivery Timeline | Create a model project plan with standard phases (Discovery, Knowledge Foundation Build, Agent Design, Integration, UAT, Go-Live), milestones, resource loading, and risk register templates. | Delivery Lead |  |  |  | ██████ | Complete | 04_Solution_Deliverables/21_Sample_Project_Plan_and_Delivery_Timeline.xlsx
CODE & DEVELOPMENT TEMPLATES
22 | Code & Templates | Knowledge Ingestion Pipeline Templates | Production-ready, parameterized code for enterprise knowledge ingestion: document parsers, metadata extractors, Snowflake/Databricks connectors, and collaboration platform adapters (SharePoint, OneDrive, Salesforce). | Sr. Data Engineer |  | ██████ | ██████ |  | Complete | 05_Code_and_Templates/22_Knowledge_Ingestion_Pipeline_Templates.docx
23 | Code & Templates | Semantic Search & RAG Retrieval Patterns | Reusable vector embedding pipelines, semantic search implementations, and RAG retrieval patterns using OpenAI, LangGraph, and vector databases with configurable chunking and ranking strategies. | AI Engineer |  |  | ██████ | ██████ | Complete | 05_Code_and_Templates/23_Semantic_Search_and_RAG_Retrieval_Patterns.docx
24 | Code & Templates | Multi-Agent Orchestration Code Library | Versioned library of agent orchestration patterns: agent routing, tool-use chains, memory management, multi-agent coordination, and fallback handling using LangGraph. | AI Engineer |  |  | ██████ | ██████ | Complete | 05_Code_and_Templates/24_Multi_Agent_Orchestration_Code_Library.docx
25 | Code & Templates | Knowledge Graph & Semantic Model Templates | Reusable knowledge graph construction scripts, taxonomy builders, and semantic relationship mappers with enterprise metadata integration hooks. | Data Engineer |  |  |  | ██████ | Complete | 05_Code_and_Templates/25_Knowledge_Graph_and_Semantic_Model_Templates.docx
26 | Code & Templates | Governance & Access Control Templates | Standard role-based access control configurations, audit logging scripts, data governance policy enforcement modules, and agent safety boundary implementations. | Platform Engineer |  |  | ██████ | ██████ | Complete | 05_Code_and_Templates/26_Governance_and_Access_Control_Templates.docx
LEARNING MODULES
27 | Learning Modules | Sales Enablement Training (Offering Overview) | 60-minute e-learning module: offering narrative, ICP walkthrough, pricing/packaging, discovery questions, objection handling. Include quiz and certification. | Sales Enablement |  | ██████ | ██████ |  | Complete | 06_Learning_Modules/27_Sales_Enablement_Training.pptx
28 | Learning Modules | Technical Pre-Sales Training (Architecture Deep-Dive) | Hands-on workshop module: knowledge layer architecture walkthrough, semantic modeling demo, RAG retrieval patterns, agent orchestration overview, and live Q&A with solutions architects. | Solutions Architect |  |  | ██████ | ██████ | Not Started
29 | Learning Modules | Agent Design & Orchestration Demo Workshop | Lab-based module where SEs can demo multi-agent orchestration, knowledge retrieval accuracy, agent governance controls, and performance monitoring in a sandbox environment. | AI Engineer |  |  |  | ██████ | Not Started
30 | Learning Modules | Client Knowledge Transfer Curriculum | Structured handover package: slide decks, lab exercises, runbooks, and assessment criteria for enabling client teams to manage and extend the Agentic Knowledge Platform post-deployment. | Delivery Lead |  |  |  | ██████ | Not Started
CATALOGING & SELECTING BEST-OF-BEST OFFERING ASSETS
31 | Asset Cataloging | Define Repository Structure & Taxonomy | Establish folder hierarchy, naming conventions, version control standards, and metadata schema for the master GTM repository. Set up on SharePoint/Confluence/GitHub. | Knowledge Mgmt Lead | ██████ |  |  |  | Not Started
32 | Asset Cataloging | Asset Quality Scoring Rubric | Create a weighted scoring matrix: relevance to offering (30%), reusability (25%), production-readiness (20%), client impact evidence (15%), visual quality (10%). Define minimum thresholds for inclusion. | Practice Lead | ██████ | ██████ |  |  | Not Started
33 | Asset Cataloging | Score, Tag & Rank All Collected Assets | Apply the rubric to every asset produced across all workstreams. Tag with metadata (workstream, vertical, asset type, maturity level). Rank and identify top-tier assets for the best-of-best collection. | Knowledge Mgmt Lead |  | ██████ | ██████ | ██████ | Not Started
34 | Asset Cataloging | Publish Best-of-Best Repository (v1.0) | Launch the curated repository with a searchable index, quick-start guide, and onboarding walkthrough for the sales and delivery teams. | GTM Lead |  |  |  | ██████ | Not Started
35 | Asset Cataloging | Governance, Refresh & Contribution Process | Define quarterly review cadence, asset retirement rules, contribution guidelines, and ownership model for ongoing repository maintenance and updates. | Practice Lead |  |  |  | ██████ | Not Started
| Update note: | 22 of 35 tasks completed (items 1-15, 19, 21-27). Files saved under 'Offering Materials/' subfolder. Items 16-18, 20, 28-35 remain Not Started by design.
| Update note: | 22 of 35 tasks completed (items 1-15, 19, 21-27). Files saved under 'Offering Materials/' subfolder. Items 16-18, 20, 28-35 remain Not Started by design.

## Summary Timeline
Sales Offering Content — 4-Month Summary Timeline
Workstream | Tasks | Month 1 | Month 2 | Month 3 | Month 4 | Key Deliverables at Completion
Offering Master Playbook | 6 | ████ | ████ |  |  | Narrative, ICP, pricing, battle cards, objection guide
Proposal Materials | 6 | ████ | ████ | ████ |  | Pitch deck, tech deck, SOW, ROI calculator, one-pagers, email templates
Case Studies & Proof Points | 5 | ████ | ████ | ████ |  | 3+ case studies, snapshots, architecture diagrams, quote bank
Best Solution Deliverables | 4 | ████ | ████ | ████ | ████ | HLD/LLD templates, vertical starter kits, sample project plan
Code & Dev Templates | 5 |  | ████ | ████ | ████ | Ingestion, RAG, agent orchestration, knowledge graph, governance code libraries
Learning Modules | 4 |  | ████ | ████ | ████ | Sales training, tech workshop, demo lab, client curriculum
Asset Cataloging & Best-of-Best | 5 | ████ | ████ | ████ | ████ | Scored repository v1.0 with governance process
TOTAL: 35 Tasks across 7 Workstreams
MONTHLY FOCUS AREAS
Month 1 FOUNDATION & DISCOVERY | Establish repository structure & scoring rubric, define offering narrative & ICP, begin collecting deliverables and interviewing project champions, kick off executive pitch deck.
Month 2 CORE CONTENT BUILD | Complete playbook components (pricing, discovery playbook), write case studies, build proposal templates and SOW, start code template development for knowledge ingestion and retrieval patterns.
Month 3 ADVANCED CONTENT & POLISH | Finalize ROI calculator, complete agent orchestration and governance code libraries, build demo workshops, score and rank all collected assets, complete vertical one-pagers.
Month 4 PUBLISH & ENABLE | Publish best-of-best repository v1.0, complete all learning modules, finalize governance & refresh process, deliver client knowledge transfer curriculum, launch sales enablement certification.