## Slide 1
November 2025
NCL Steering Committee
Project Update
and Strategic Review

## Slide 2
Meeting Agenda
01
Progress recap
02
Key observations and recommendations
03
Plan for the month ahead
04
Golden process alignment
05
Innovation opportunities
06
Feedback and discussion

## Slide 3
Progress Recap
Key accomplishments achieved to date:
SnowflakeML environment validated and configured
Source system connections established (Prospect, Guest, Booking)
Initial MLOps framework drafted (Git branching, CI patterns, job orchestration)
Feature store blueprint designed with priority features identified
Model inventory completed across Marketing, Revenue, and Operations
Migration approach finalized (R to Snowpark Python/Snowflake ML)
Golden process alignment sessions completed with DS and DE teams

## Slide 4
Environment Observations and Recommendations
What we're seeing:
Fragmented R codebase with inconsistent structures
Feature logic duplicated across tables and scripts
Manual refresh processes limiting retraining cadence
Access permissions not aligned with RBAC best practices
Areas of concern:
Legacy R packages incompatible with SnowflakeML
Missing lineage documentation slowing migration
Ambiguous model ownership for three marketing models
Recommended actions:
Standardize feature logic within the Snowflake Feature Store
Implement role-based access control across environments
Document model metadata and lineage
Confirm ownership and SME for each Tier 1 and Tier 2 model

## Slide 5: Key Observations
Data architecture:
Schema inconsistencies limiting reproducibility
Need to shift toward bronze–silver–gold structure
Resource utilization:
Warehouse sizing shows overprovisioned dev environments
Opportunity to reduce compute costs by 25–35 percent
Governance and security:
RBAC taxonomy incomplete
Model approval workflow not consistently followed
Model card and risk-tiering not yet embedded
+
+
Misalignment across data architecture, warehouse usage, and governance slowing ML migration.
The Challenge
ML Operations Foundations
Execution Foundations
Standardized data layers
Governed architecture
Consistent access control
Unified model lifecycle

## Slide 6
Model Inventory Summary
14
Total Models
6
Priority Models
(Out of 14)
Current Focus:
Einstein Contact Models (RSSC & OCI)
Risk Tier Breakdown
Tier 1
2 Models (High Risk)
Tier 2
8 Models (Medium Risk)
Tier 3
4 Models (Low Risk)
Priority Model List
Einstein Contact Models (RSSC & OCI)
Status: In Progress
Prospect Sales
Guest Upsell Propensity
Revenue Forecast
Cancellation Propensity
Migration Status
Discovery
Completed: inventory and scope finalized.
R-to-Python translation
Completed for Einstein models.
Business logic validation
Upcoming: business logic and outputs verified.
Feature alignment
In progress: align features and interfaces with platform.
Deployment
Upcoming: rollout to OCI environments and monitor.

## Slide 7
Month-Ahead Project Plan
1
Week 1–2
Finalize CI/CD pipelines for training and scoring
Set up initial feature store tables
Refactor two R models to Snowpark-compatible versions
2
Week 3–4
3
Week 5–6
Automate model training workflows
Implement monitoring dashboards (performance + drift)
Complete validation pack for first migrated model
Move migrated models into staging
System stabilization and performance tuning
Finalize Golden Process v1 documentation

## Slide 8
Golden Process Framework
Intake
Structured request intake
Clear success metrics
Model risk classification
Development
Refactoring R models into Snowpark Python
Integrating features into the feature store
Version-controlled workflows
Testing
Statistical validation
Drift analysis
Model card creation
Deployment
CI-driven promotion
Rollback strategy implemented
Model registry tagging and lineage tracking

## Slide 9
Innovation Opportunities
Feature Store
Centralizing feature logic to improve reuse and auditing
Snowpark Container Services
Support for custom R logic and hybrid runtimes during transition
Dynamic Tables
Automated data refresh and retraining triggers
Cortex AI
LLM-powered applications for guest personalization and content analysis
Innovation
Feature Store
Snowpark Container Services
Dynamic Tables

## Slide 10
How Are We Doing
88%
On-time delivery
Slight delays due to environment access approvals
90%
Stakeholder satisfaction
Strong cross-team alignment and responsiveness
94%
Quality metrics
All completed components meeting standards

## Slide 11
Next Steps
Confirm sequencing of priority model migrations
Finalize RBAC roles and permissions
Approve CI/CD environment changes
Schedule feature store deep-dive with DS and DE teams

## Slide 12
Open Discussion
What's working well?
Where should we deepen focus?
Any blockers requiring SteerCo support?
©